## Assignment requirements
SamSum Assignment 1 - Requirement Status
Status reflects repository code and saved evidence reviewed on 27 Oct 2026. ?Done? means evidence exists; final report/demo packaging may still be required.
# | Assignment requirement | Status | Evidence found | What remains / notes
1 | Problem definition and application scenario | Done | SAMSum conversation summarization and action-item extraction are described in README.md and documents/03_Implementation_and_Experiments/01_High_Level_Architecture.md. | No major implementation work identified. Ensure final report states target user, input/output, and why an LLM is appropriate.
2 | Dataset understanding, fields, sample size, preparation, and subset | Done - verify attribution | Raw/processed splits are present locally; validation/preprocessing scripts and documents/03_Implementation_and_Experiments/Data_Quality_Report.md record data handling. | Record dataset source/version/license and attribution in the final submission; report the exact experimental subsets used.
3 | Compare at least three generative-model families and justify causal LM choice | Partial | Three configurations (Qwen, FLAN-T5, DistilBART) and 50-sample metrics are documented under documents/03_Implementation_and_Experiments/05_Model_Family_Comparison/ and outputs/model_comparison_50_samples/. | FLAN-T5 and DistilBART are both encoder-decoder/seq2seq models, so the comparison does not clearly establish three distinct families. Add the course family landscape and project-specific causal-LM rationale to the final report.
4 | Explain tokenization, embeddings, Transformer/attention, LM head, and autoregressive generation | Pending | The tokenizer and pretrained model are used in implementation, but no final report section with the required explanation was identified. | Write an explanation connecting these components and next-token generation to the project workflow.
5 | Pretrained Hugging Face causal-LM baseline with at least three outputs | Done | Qwen baseline outputs and metadata: outputs/baseline_smoke_test/baseline_outputs.json and outputs/baseline_smoke_test/run_metadata.json (3 training examples). | Present as qualitative pipeline verification, not a formal performance evaluation.
6 | Compare zero-shot, few-shot, role/context, and constraint prompts | Done - small sample | Templates in src/prompts.py; generated comparisons in outputs/prompt_experiments/prompt_comparison.csv; manual criteria in outputs/evaluation/. | Only 3 examples per strategy were scored. State this limitation and avoid broad claims.
7 | Compare greedy and sampling with temperature and at least one of top-k/top-p | Done | Implementation in src/run_decoding_experiments.py; runs and variability summaries in outputs/decoding_experiments/. | Summarize observed output quality/variability and settings in the final report.
8 | Compare prompting, RAG, fine-tuning/PEFT and justify the selected approach | Pending in final report | No project-specific comparison in a final report was identified. Actual fine-tuning is optional per the assignment. | Add a concise trade-off comparison and explain why the chosen strategy fits SAMSum and project constraints.
9 | Machine-readable output schema and validation | Done | Schema, parsing/validation code, generated outputs, and tests: src/structured_schema.py, src/run_structured_output.py, src/test_structured_schema.py, outputs/structured_output/. | Include schema and representative validated outputs in report/appendix. Clarify that schema validity does not prove factual correctness.
10 | Useful tool/function definition and representative invocation | Done | Allowlisted validation tool in src/run_tool_calling.py; tests in src/test_tool_calling.py; example in outputs/tool_calling/tool_calling_demo.json. | Describe accurately as application-level JSON tool-call protocol, not native model-specific tool calling; note there is no tool-result follow-up model turn.
11 | Reusable prompt template and programmatic/parameterized generation | Done | Reusable functions in src/prompts.py accept dialogue input and are used by experiment runners. | Show a representative template and invocation in the report or demonstration.
12 | Evaluate with at least four criteria and provide failure/error analysis | Partial | Four human-scored criteria and comparison in outputs/evaluation/; ROUGE/runtime metrics in outputs/model_comparison_50_samples/; unsupported-content cases in documents/03_Implementation_and_Experiments/04_Experiment_and_Decision_Log.md. | Consolidate method, results, and at least 3 concrete failure cases in the final report. Explain the small prompt sample and that ROUGE is not factuality.
13 | Responsible-use risks and practical controls | Partial | Prompts constrain unsupported claims; schema validation and human-review warning appear in implementation/evidence. | Add an explicit report section covering hallucination/faithfulness, privacy, misuse, data leakage, and reliability controls relevant to this application.